## Sheet1
Id | Task | Area | State | Estimate | Time | Overcost | When Started | When Completed | State | To Do
1 | Loto649 prototype | Core | Done | 1.5 | 1.5 | 0
2 | loto649 mvp | Core | Done | 2 | 3 | 1 |  |  | Row Labels | Sum of Estimate
4 | Sort results of loto 649 | Core | Done | 0.5 | 0.17 | -0.33 |  |  | Core
5 | GameCore Design | Core | Done | 3 | 2 | -1 |  |  | Research java file reader | 0.5
7 | Abstract GameResult | Core | Done | 1 | 0.5 | -0.5 |  |  | Implement file with configs | 2
8 | Loto 649 GameResult concrete | Core | Done | 1 | 1 | 0 |  |  | Research multithreading | 2
14 | Loto Session abstract | Core | Done | 0.5 | 0.17 | -0.33 |  |  | Do GameCore skeleton | 1
15 | Loto 649 Session concrete | Core | Done | 0.17 | 0.34 | 0.17 |  |  | Data
16 | Integrate GameResult in 649Session | Core | Done | 0.5 | 1 | 0.5 |  |  | DB Schema | 1
17 | Research java file reader | Core | To Do | 0.5 |  | -0.5 |  |  | DbOps read connection details and connect | 0.5
18 | Implement file with configs | Core | To Do | 2 |  |  |  |  | DbOps check results against DB | 3
19 | Research multithreading | Core | To Do | 2 |  |  |  |  | DbOps save checks | 1
25 | Do GameCore skeleton | Core | To Do | 1 | 0.3 |  |  |  | Research SQLite operations | 1.5
6 | Research Sqlite | Data | Done | 1 | 1 | 0 |  |  | View to show games in one line | 0.5
9 | GameDb design | Data | Done | 1 | 0.3 | -0.7 |  |  | Query to check results for Loto 649 session | 0.5
12 | DB Schema | Data | To Do | 1 | 0.6 | -0.4 |  |  | Mailer
21 | DbOps read connection details and connect | Data | To Do | 0.5 | 0.17 | -0.33 |  |  | GameMailer: design | 2
22 | Dbops Save LotoSession with results | Data | Done | 1 | 0.66 | -0.34 |  |  | Mgm
23 | DbOps check results against DB | Data | To Do | 3 |  | -3 |  |  | Research on path operations in eclipse | 0.5
24 | DbOps save checks | Data | To Do | 1 |  | -1 |  |  | Testing
26 | Research SQLite operations | Data | To Do | 1.5 | 0.17 | -1.33 |  |  | Research Java Tester | 3
27 | Key generator for system | Data | Done | 1 | 0.3 | -0.7 |  |  | Grand Total | 19
28 | View to show games in one line | Data | To Do | 0.5
29 | Query to check results for Loto 649 session | Data | To Do | 0.5
10 | GameMailer: design | Mailer | To Do | 2 |  | -2
3 | Research management method and estimates | Mgm | Done | 1 | 3 | 2
13 | Move project to eclipse | Mgm | Done | 0.5 | 0.75 | 0.25
20 | Research on path operations in eclipse | Mgm | To Do | 0.5 |  | -0.5
11 | Research Java Tester | Testing | To Do | 3 |  | -3