## Sheet1
Id | Task | Area | State | Estimate | Time | Overcost | When Started | When Completed | State | (Multiple Items)
1 | Loto649 prototype | Core | Done | 1.5 | 1.5 | 0
2 | loto649 mvp | Core | Done | 2 | 3 | 1 |  |  | Row Labels | Sum of Estimate
3 | Research management method and estimates | Mgm | Done | 1 | 3 | 2 |  |  | Core
4 | Sort results of loto 649 | Core | Done | 0.5 | 0.17 | -0.33 |  |  | Abstract GameResult | 1
5 | GameCore Design | Core | Ongoing | 5 | 2 | -3 |  |  | GameCore Design | 5
6 | Research Sqlite | Data | Done | 1 | 1 | 0 |  |  | Loto 649 GameResult concrete | 1
7 | Abstract GameResult | Core | In Progress | 1 | 0.17 | -0.83 |  |  | Data
8 | Loto 649 GameResult concrete | Core | In Progress | 1 |  | -1 |  |  | DB Schema | 1
9 | GameDb skeleton | Data | To Do | 1 |  | -1 |  |  | GameDb skeleton | 1
10 | GameMailer: design | Mailer | To Do | 2 |  | -2 |  |  | Mailer
11 | Research Java Tester | Testing | To Do | 3 |  | -3 |  |  | GameMailer: design | 2
12 | DB Schema | Data | To Do | 1 |  | -1 |  |  | Testing
[9 empty] | Research Java Tester | 3
[9 empty] | Grand Total | 14