## Sheet1
Id | Task | Area | State | Estimate | Time | Overcost | When Started | When Completed | State | To Do
1 | Loto649 prototype | Core | Done | 1.5 | 1.5 | 0
2 | loto649 mvp | Core | Done | 2 | 3 | 1 |  |  | Row Labels | Sum of Estimate
3 | Research management method and estimates | Mgm | Done | 1 | 3 | 2 |  |  | Core
4 | Sort results of loto 649 | Core | Done | 0.5 | 0.17 | -0.33 |  |  | Research java file reader | 0.5
5 | GameCore Components list/design | Design | Done | 3 | 2 | -1 |  |  | Implement file with configs | 2
6 | Research Sqlite | Data | Done | 1 | 1 | 0 |  |  | Research multithreading | 2
7 | Abstract GameResult | Core | Done | 1 | 0.5 | -0.5 |  |  | Do GameCore skeleton & Use cases | 1
8 | Loto 649 GameResult concrete | Core | Done | 1 | 1 | 0 |  |  | 649 Archive refill | 1
9 | GameDb design | Design | Done | 1 | 0.3 | -0.7 |  |  | Data
10 | GameMailer: design | Mailer | To Do | 2 |  | -2 |  |  | DB Schema | 1
11 | Research Java Tester | Testing | To Do | 3 |  | -3 |  |  | DbOps read connection details and connect | 0.5
12 | DB Schema | Data | To Do | 1 | 0.6 | -0.4 |  |  | DbOps check results against DB | 3
13 | Move project to eclipse | Mgm | Done | 0.5 | 0.75 | 0.25 |  |  | DbOps save checks | 1
14 | Loto Session abstract | Core | Done | 0.5 | 0.17 | -0.33 |  |  | Research SQLite operations | 1.5
15 | Loto 649 Session concrete | Core | Done | 0.17 | 0.34 | 0.17 |  |  | Import Loto archive | 1
16 | Integrate GameResult in 649Session | Core | Done | 0.5 | 1 | 0.5 |  |  | Query to check plays vs results | 0.5
17 | Research java file reader | Core | To Do | 0.5 |  | -0.5 |  |  | Mailer
18 | Implement file with configs | Core | To Do | 2 |  | -2 |  |  | GameMailer: design | 2
19 | Research multithreading | Core | To Do | 2 |  | -2 |  |  | Mgm
20 | Research on path operations in eclipse | Mgm | To Do | 0.5 |  | -0.5 |  |  | Research on path operations in eclipse | 0.5
21 | DbOps read connection details and connect | Data | To Do | 0.5 | 0.17 | -0.33 |  |  | Testing
22 | Dbops Save LotoSession with results | Data | Done | 1 | 0.66 | -0.34 |  |  | Research Java Tester | 3
23 | DbOps check results against DB | Data | To Do | 3 |  | -3 |  |  | Design
24 | DbOps save checks | Data | To Do | 1 |  | -1 |  |  | Base Use cases list | 1
25 | Do GameCore skeleton & Use cases | Core | To Do | 1 | 0.3 | -0.7 |  |  | Grand Total | 21.5
26 | Research SQLite operations | Data | To Do | 1.5 | 0.17 | -1.33
27 | Key generator for system | Data | Done | 1 | 0.3 | -0.7
28 | View to show games in one line | Data | Done | 0.5 | 0.5 | 0
29 | Query to check results for Loto 649 session | Data | Done | 0.5 | 0.5 | 0
30 | Import Loto archive | Data | To Do | 1 |  | -1
31 | Query to check plays vs results | Data | To Do | 0.5 | 0.5 | 0
32 | Research web crawling in java | Core | Done | 1 | 0.6 | -0.4
33 | Implement Archive 649 update | Core | Done | 2 | 2.2 | 0.2
34 | 649 Archive refill | Core | To Do | 1 |  | -1
35 | Base Use cases list | Design | To Do | 1 |  | -1